## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | All In-One Mentoring Sysytem |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT GUIDE |  | Prof. Sachin Takmare |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Problem search | Sahil, Yash, Vedang, Itisha | 2021-09-16 | 2021-09-06 | 1 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Problem finalization | Sahil, Yash, Vedang, Itisha | 2021-09-16 | 2021-09-06 | 1 | 100% | bar: WEEK 2 W
1.2 | Project Title | Sahil | 2021-09-16 | 2021-09-09 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Vedang, Sahil, Itisha | 2021-09-16 | 2021-09-26 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Problem Definition | Sahil,Itisha | 2021-09-17 | 2021-09-27 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Objectives | Itisha | 2021-09-23 | 2021-09-28 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Scope | Sahil, Vedang | 2021-09-29 | 2021-09-29 | 1 | 100% | bar: WEEK 3 F
1.7 | Existing System/Project | Sahil, Yash, Vedang, Itisha | 2021-09-30 | 2021-09-30 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Sahil, Yash, Vedang, Itisha | 2021-10-02 | 2021-10-02 | 1 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Yash,Itisha | 2021-10-03 | 2021-10-03 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Yash | 2021-10-05 | 2021-10-05 | 1 | 100% | bar: WEEK 3 F
1.11 | Applications | Itisha, Sahil | 2021-10-06 | 2021-10-07 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Sahil, Yash | 2021-10-07 | 2021-10-08 | 1 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Sahil | 2021-10-08 | 2021-10-09 | 1 | 100% | bar: WEEK 4 F to WEEK 6 T
2.3 | Data Flow Diagram | Sahil | 2021-10-09 | 2021-10-09 | 1 | 100% | bar: WEEK 6 T to WEEK 6 W
2.4 | Modules | Sahil, Yash, Vedang, Itisha | 2021-10-10 | 2021-10-10 | 1 | 100% | bar: WEEK 6 W to WEEK 6 F
2.4.1 | Module-1 | Sahil | 2021-10-10 | 2021-10-10 | 1 | 100% | bar: WEEK 6 F
2.4.2 | Module-2 | Sahil | 2021-10-11 | 2021-10-11 | 1 | 100% | bar: WEEK 6 F
2.4.3 | Module-3 | Yash | 2021-10-11 | 2021-10-11 | 1 | 0% | bar: WEEK 6 R to WEEK 6 F
2.5 | Preparation Of Report | Itisha, Sahil, Vedang | 2021-11-15 | 2021-11-25 | 1 | 100% | bar: WEEK 6 F
3 | Project Implementation
3.1 | Module-1 | Sahil, Itisha | 2021-11-10 | 2021-11-14 | 0 | 100% | bar: WEEK 7 M to WEEK 7 F
3.2 | Module-2 | Vedang |  |  | 0 | 100% | bar: WEEK 7 F to WEEK 8 F
3.3 | Module-3 | NONE |  |  | 0 | 0% | bar: WEEK 8 W to WEEK 8 F
3.4 | Module-4 | NONE |  |  | 0 | 0% | bar: WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Sahil, Yash, Vedang, Itisha | 2021-11-20 | 2021-11-21 | 0 | 100% | bar: WEEK 10 T to WEEK 10 F
4.2 | Testing | Sahil, Yash, Vedang, Itisha | 2021-11-21 | 2021-11-22 | 0 | 100% | bar: WEEK 10 W to WEEK 10 F
5 | Results and Analysis
5.1 | Analysis Of Results | Sahil, Yash, Vedang, Itisha | 2021-11-27 | 2021-11-29 | 0 | 100% | bar: WEEK 11 M to WEEK 11 W
5.2 | Graphical Representation | Sahil, Yash, Vedang, Itisha | 2021-11-30 | 2021-11-30 | 0 | 100% | bar: WEEK 11 W
5.3 | Report Preparation | Sahil, Yash, Vedang, Itisha